## Tabellenblatt1
Risk Name | Risk Description | Risk Probability of Occurence | Risk Impact | Risk Factor | Risk Mitigation | Person in Charge of Tracking
session hijacking | The Session of a user gets hijacked | 1% | 9 | 0.09 | Giving the session-tokens an expire-date | Lukas
Bad time estimation | Tasks takes longer than expected | 30% | 3 | 0.9 | Plan some puffer time | All
Communication Problems | Missunderstanding of expectations | 25% | 5 | 1.25 | Communicate as often as possible, don't assume anything | Benedikt
User doesn't like the product | The User is not happy with the end product | 15% | 9 | 1.35 | Asking the potential users for preferences and ideas while developing | All
Github goes offline | Github and therefore all backup are lost | 1% | 10 | 0.1 | Always keep local backups | Nils
Data Loss | Developer didn't use VCS | 5% | 8 | 0.4 | regularly backing up the project | Nils